Current Needs: 	1) Execution of Memorandum of Agreement by NCDOT, NCSHPO, and FTA; 2) FTA approval of Environmental Assessment and Finding of No Significant Impact (FONSI)

Status: 		FTA reviewing Environmental Assessment.  Parcel appraisals completed.  No public controversy or community opposition to preferred site.  Staff has scheduled informational meeting for property owners for December 12, 2009.

Public Communication:		Dedicated project web site maintained by City staff---www.greatnc.com.  Public meetings and periodic written communication with property owners.

Intermodal Center Site:	 Uptown Greenville, bounded by Evans St., East 8th St., Cotanche St., and East 9th St.  Twenty-one parcels, three of which are either State owned or owned by the City.  Eighteen parcels controlled by thirteen property owners.

Project Issues:	Historic property for architecture---Jones Lee House; two off site parcels that would likely qualify for National Register for Historic Places.  Impact mitigation efforts outlined in Memorandum of Agreement.

Federal Earmarks:

Expansion Buses and Intermodal Center			FFY 2007 	E2007 BUSP-366 	$715,081

Expansion Buses and Intermodal Center			FFY 2008	E2008 BUSP-365	$774,671

Expansion Buses and Intermodal Center			FFY 2009	E2009 BUSP-533	$804,466

Available for Land Acquisition and Design		Total			$2,294,218 plus Local and State Match – 20%

Project Cost Estimate based on (STIP)

Federal							$4,800,000

Local							$600,000

State							$600,000

Total							$6,000,000

Current Construction Estimate (Moser Mayer Phoenix 2009)

Land/Acquisition/Demolition & Environmental 		$2,928,000

Design/Surveys						$710,879

Construction/FFE/Contingency				$7,279,902

Total							$10,936,781

Community Involvement: 	Public comment at City Council meetings, public input meetings, Steering Committee meetings, dedicated project website, information on Greenville Government Access Channel and notices published in local daily newspaper.

Aerial View of Intermodal Center Site

Administrative Project Manager:	Thomas M. Moton, Jr., Assistant City Manager

Email:	tmoton@greenvillenc.gov

Office:	252.29-4432

GREAT Transit Manager:		Nancy Harrington

Email: 	nharrington@greenvillenc.gov

Office:	252.329-4047

Doc. 849492v2